## Sheet1
S.No | Milestone Name | Task | Testing | Status | Internal Deadline | Customer Deadline
1 | Initial Release | 1. UI and API beta release | Manual | Ongoing | 11th October | 14th October
|  | 2. Code Integration with GUI | Manual
|  | 3. Workspace Detection, Line Detection | Accuracy > 90%
|  | 4. Character Segmentation | Accuracy > 90%
2 | Model Development | 1. Model Development and Testing 1 |  |  | 28th October | 1st November
|  | 2. Character Recognition | Accuracy > 80%
|  | 3. Line Analysis and Box drawing | Accuracy > 80%
3 | Improvisation | 1. Model Improvisation |  |  | 11th November | 15th November
|  | 2. Code Tuning | Accuracy > 90%
|  | 3. Python Package Development | Manual
4 | Finishing and Delivery | Delivery and Handover code |  |  | 26th November | 29th November