## Sheet1
S.No | Milestone Name | Task | Testing | Status | Deadline
1 | First Review | 1. UI and API beta version | Manual | Ongoing | 1st October
|  | 2. Code Integration with GUI | Manual
|  | 3. Workspace Detection, Line Detection | Accuracy > 90%
|  | 4. Character Segmentation | Accuracy > 90%
2 | Model Development | 1. Model Development and Testing 1 |  |  | 18th October
|  | 2. Character Recognition | Accuracy > 80%
|  | 3. Expression Execution. | Accuracy > 80%
4. Expression Box.
3 | Release | 1. Model Improvisation |  |  | 11th November
|  | 2. Code Tuning | Accuracy > 90%
|  | 3. Python Package wrapping | Manual
4. Delivery and Handover code.
4 | Follow up Call | Feedback |  |  | 20th November